# Ditch Management Checklist (Improvement)

RE:  Minn. Stat. § 103E

________________		___________________________________

Ditch No.				Commissioner’s District

___________   Petition and bond received from landowners for improvement________________________________

103E.202 – 103E.235                  				          name

___________   Petition and bond fwd’d to County Attorney for review (The county attorney must review the petition and bond  	           within 30 days after it is filed)	103E.238

___________   Petition and bond returned to Land Records, if adequate; if inadequate, it is returned to petitioners by the County

Attorney with a description of the deficiencies		103E.238

___________   Schedule the board appearance w/Bob to present petition to Board.  (The auditor shall present the petition to the 	            board at its next meeting)   103E.215

___________   Notify County Commissioner of the petition and the upcoming discussion

___________   Board appoints engineer (within 30 days after receiving the

petition) ____________________________	103E.241

___________    Bond and Oath received from the engineer.  103E.241

___________   Following survey of the proposed drainage project, engineer files preliminary report w/Land Records

and copies the DNR		103E.251

___________   Schedule preliminary hearing no more than 30 days after the date of the order (include enough time

for mailings—to be mailed at least 10 days before the hearing)	103E.261

___________   Mail notice of preliminary hearing to landowners affected by the drainage project (including

property owners, political subdivision, etc.)	    		103E.261

If it includes a repair, mail to all within the ditch system

___________   Although not a statutory requirement, notice of preliminary hearing may be published and/or posted; consult

County Commissioner

Newspaper(s) _______________________________	Dates published_____________________________

___________   Ensure the preliminary DNR report has been received; if it hasn’t follow up with the local DNR office

___________   Prepare preliminary hearing agenda

___________   Attend preliminary hearing

- Confirm that all legal requirements have been met (i.e. mailing of notices, receipt of DNR advisory report—if rec’d, etc.).  If DNR report is rec’d, it must be read into the record. 103E.261, subd. 2 & 3

- Sufficiency of petition—County Atty comments on sufficiency of petition at the prelim hearing

- Board Action:

- viewers are appointed

- engineer directed to prepare detailed survey report (final report)

___________ Within 5 days after the engineer’s final report is filed, schedule a meeting w/viewers and provide them with a

copy of the order appointing them; also complete the oath... (See files)		103E.305, subd. 2 & 3

NOTE:  In practice, viewers meet shortly after they are appointed, typically before the engr’s final report is rec’d.

___________  Viewers prepare and file a report (viewers’ report)	103E.321

___________  DNR examines the engineer’s final report and makes a final advisory report within 30 days of receipt of

the final report by the drainage authority		103E.301

___________   Following receipt of engineer’s final report, viewers’ report, and DNR report (if rec’d), schedule final hearing date

(25 to 50 days after the first date of publication of the final hearing notice) w/Dave_______________103E.285 &

103E.291, and 103E.325, subd. 1					                     hearing date

___________   Following receipt of the viewers’ report and the DNR report, prepare owner’s report from the viewers’ report

within 30 days after it is filed	103E.323

___________  Mail a copy of the owner’s report to each property owner affected by the proposed drainage project, notify County

Board, auditors of affected counties, and all interested persons of the time and location of the final hearing by

publication, posting, and mail			103E.325

NOTE:  Notices are to be mailed within 1 week after the notice is first published in the paper.

___________   Provide a copy of the final hearing notice to Jody for posting (must be posted at least 3 weeks before the date of

the final hearing at the front door of the courthouse)		103E.325

___________   Publish the final hearing notice once per week for 3 consecutive weeks in a legal newspaper of general circulation	           in each county affected by the notice (usually the Free Press and one newspaper located in general area of ditch)

Newspaper(s) _______________________________	Dates published_____________________________

___________   Following publication, the publisher should return an affidavit of publication for the ditch file

___________   File posted notice, property owner’s report, affidavit of publication, final hearing notice, etc. in ditch file before

final hearing

___________   Prepare final hearing agenda

___________   Final Hearing

- Confirm that all legal requirements have been met (i.e. mailing of notices, receipt of DNR advisory report—if rec’d, etc.).  If DNR report is rec’d, it must be read into the record.

- Board Action:

- adopt and confirm the viewers’ and engineer’s reports as made or amended

- establish the proposed drainage project

- adopt resolution relating to financing

- Determine if damages are to be paid; pay damages or deduct from payment before construction begins?? (see 103E.515)

In practice, we have waited until the appeal period is up before damages are paid.

# CONSTRUCTION OF DRAINAGE PROJECT (103E.501 – 103E.555)

__________   Schedule the bid opening (leave enough time for publication) and bid award (letting)—allow 30 days for appeal

period to expire; bid award should be scheduled during the next board meeting following the bid opening

Bid Opening_______________________		Bid Award________________________

Note:  The bid award is set for the next board meeting, following the bid opening; notify Jody to get on board

agenda

__________   Engineer prepares specs and advertises for construction bids in the construction bulletin

__________   Publish advertisement for bids in the legal newspaper (Free Press), and in the newspaper in the town near where the

ditch is located.   ***publish for each week for 3 consecutive weeks (cannot be published during the same

week as the bid opening) ***

***Bids must remain sealed until the day and time of the bid opening.  At the bid opening, bids are publicly opened and read.  A bid bond or a certified check must accompany the bid***

__________   Hold bid opening (Land Records Director, ditch manager, and engineer attend); after the opening, the engineer

takes all bids to his office for review

__________   Hold bid award (the Land Records Director, ditch manager, and engineer attend the next board meeting, following

the bid opening); following his review of the bids, the engineer recommends the low bidder for award of the

contract

Board moves to award the contract to the low bidder

# of bids received________________	  Low bidder and bid________________________________________

Tentative start date_________________________

Tentative completion date___________________

__________   Bid award processing—forward letters to unsuccessful bidders

__________   Contractor constructs the drainage project; the engineer oversees this process

NOTE:  When paying bills for the drainage project, retain the final payment (about 10% of total cost) until after

the ditch work is complete and approved by the engineer.

__________   Engineer contacts Land Records when the process is complete

__________   Issue and Sell bonds (Jerry and Dave handle this item)

__________   Schedule a completion hearing, following the completion hearing, following the completion of the construction of

the drainage project

__________   Provide notice of hearing to the affected landowners by publication or notice by mail at least 10 days before the

hearing	103E.555

The notice should state that

- the engineer’s survey and inspection report is filed?

- the time and location of the hearing

- a party objecting to the acceptance of the contract may appear and be heard

__________  IC 134 received from the contractor.  (Required by State Auditor before final payment)

__________   Hold the completion hearing (to consider the engineer’s survey and inspection report on the completed drainage

project	103E.555

Board action:  direct payment of the balance due, if it determines that the contract has been completed in

accordance with the plans and specifications